## Product BackLog
HomeView
Team | Unite |  | Client
Team Leader | Eric Truong |  | V. Vong
Daniel Monge
| Christian Lam |  | Availability
| Erina Lara |  | https://lettucemeet.com/l/AWMa7
Michael Lamera
Product BackLog
ID | State | Story Name | Definition of Done | Effort Points | Priority | Responsible Party | Internal Due Date | External Due Date
7.1 | Ongoing | Central Media Library, Playlists, Blacklist | Central Media Library, Playlists, Blacklist implementations can be run with no errors | 180 | 1 | Eric Truong | 2022-04-04 | 2022-04-04
8.1 | Planned | Central Media Library, News, ActWiki, Ratings and Reviews |  | 180 | 2 | Eric Truong | 2022-04-25 | 2022-04-25
Done Pile
ID | State | Story Name | Definition of Done | Effort Points | Priority | Responsible Party | Internal Due Date | External Due Date
1 | Done! | Get Proposal Approved | Vong sends email confirmation of our approved proposal. | 0 | 0 | Eric Truong | 2021-09-17 | 2021-09-17
2 | Done! | Milestone 1 Complete BRD Complete HL Design Complete Tech Spec Complete Site Map | Vong sends email confirmation of our approved BRD. | 0 | 0 | Eric Truong | 2021-10-06 | 2021-10-06
3 | Done! | Milestone 2 Complete Network Diagram Complete Project Plan Complete Test Plan | Vong sends email confirmation of our approved Milestone 2 documents. | 0 | 0 | Eric Truong | 2021-10-27 | 2021-12-07
4.1 | Done! | Milestone 3 - Complete LL Design | Vong sends email confirmation of our approved Milestone 3 documents. | 120 | 0 | Eric Truong | 2021-12-08 | 2021-11-02
4.1.1 | Done! | User Administration LLD | Low Level Design / Error Handling Completed | 15 | 0 | Eric Truong | 2021-11-03 | 2021-11-03
4.1.2 | Done! | User Management LLD | Low Level Design / Error Handling Completed | 15 | 0 | Eric Truong | 2021-11-03 | 2021-11-03
4.1.3 | Done! | System Observability LLD | Low Level Design / Error Handling Completed | 15 | 0 | Eric Truong | 2021-11-10 | 2021-11-10
4.1.4 | Done! | Central Media Library LLD | Low Level Design / Error Handling Completed | 15 | 0 | Eric Truong | 2021-11-10 | 2021-11-10
4.1.5 | Done! | Playlists LLD | Low Level Design / Error Handling Completed | 15 | 0 | Eric Truong | 2021-11-17 | 2021-11-17
4.1.6 | Done! | Blacklists LLD | Low Level Design / Error Handling Completed | 15 | 0 | Eric Truong | 2021-11-24 | 2021-11-24
4.1.7 | Done! | Ratings and Reviews LLD | Low Level Design / Error Handling Completed | 15 | 0 | Eric Truong | 2021-12-01 | 2021-12-01
4.1.8 | Done! | ActWiki LLD | Low Level Design / Error Handling Completed | 15 | 0 | Eric Truong | 2021-12-08 | 2021-12-08
4.1.9 | Done! | News LLD | Low Level Design / Error Handling Completed | 15 | 0 | Eric Truong | 2021-12-08 | 2021-12-08
4.2 | Done! | Milestone 3 - Complete UM (User Management) | UM implementation is finished and can run with no errors. | 180 | 0 | Eric Truong | 2021-12-15 | 2021-12-15
4.2.1 | Done! | User Management Testing | All user management tests pass successfully. | 180 | 0 | Eric Truong | 2021-12-15 | 2021-12-15
4.3 | Done! | Milestone 3 - Complete Logging/Archiving | Logging/Archiving implementation is finished and can run with no errors. | 180 | 0 | Eric Truong | 2021-12-15 | 2021-12-15
4.3.1 | Done! | Logging / Archiving Testing | All logging / archiving tests pass successfully. | 180 | 0 | Eric Truong | 2021-12-15 | 2021-12-15
5.1 | Done! | User Management | UM implementation is finished and can run with no errors. | 100 | 0 | Eric Truong | 2022-02-14 | 2022-02-14
5.2 | Done! | Usage Analysis Dashboard | UAD implementation is finished and can run with no errors. | 100 | 0 | Eric Truong | 2022-02-14 | 2022-02-14
5.3 | Done! | Registration | Registration implementation is finished and can run with no errors. | 100 | 0 | Eric Truong | 2022-02-14 | 2022-02-14
5.4 | Done! | UI | UI implementations can be run with no errors. | 100 | 0 | Eric Truong | 2022-02-14 | 2022-02-14
6.1 | Done! | Authorization / Authentication / Log out / UAD | Authorization, Authentication, Log out, UAD implementation is finished and can run with no errors. | 160 | 1 | Eric Truong | 2022-03-07 | 2022-03-07

## Sprints
Sprint Cycle Time | 7 Days
[8 empty] | Sat | Sun | Mon | Tue | Wed | Thur | Fri
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Estimate | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17
1.1 | Edit Proposal | 2021-09-11 | Specify scope of web project | Changes reflect on master proposal document | Documentation | Daniel Monge | 1.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  |  | Support claim of streaming services losing revenue | Changes reflect on master proposal document | Documentation | Erina Lara | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
|  |  | Provide more detail on application features | Changes reflect on master proposal document | Documentation | Michael Lamera | 1 | 1 | 0.5 | 0 | 0 | 0 | 1 | 0
|  |  | Support statement our service allowing users to save money | Changes reflect on master proposal document | Documentation | Eric Truong | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
|  |  | Specify supported browser and version | Changes reflect on master proposal document | Documentation | Christian Lam | 1 | 0 | 0.33 | 0 | 0 | 0 | 0.33 | 0
|  |  | Feedback from client (Confirmation) | Changes reflect on master proposal document | Documentation | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Estimated effort | 5.5 | 4.7143 | 3.9286 | 3.1429 | 2.3571 | 1.5714 | 0.78571 | 0
[6 empty] | Actual effort | 5.16 | 4.16 | 2.83 | 2.83 | 2.83 | 1.83 | 0 | 0
[8 empty] | Sat | Sun | Mon | Tue | Wed | Thur | Fri
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Estimate | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24
1.2 | Edit Proposal | 2021-09-18 | Application Restrictions own section | Changes reflect on master proposal document | Documentation | Eric Truong | 3 | 0 | 0 | 0 | 2 | 0.5 | 0.5 | 0
|  |  | Specify how data will be fetched | Changes reflect on master proposal document | Documentation | Daniel Monge | 1 | 0 | 0 | 0.33 | 0 | 0.5 | 0 | 0
|  |  | How will playlists be shared | Changes reflect on master proposal document | Documentation | Michael Lamera | 1 | 0 | 0.33 | 0.5 | 0 | 0 | 0 | 0
|  |  | How will users know if playlist updated, removed, etc | Changes reflect on master proposal document | Documentation | Erina Lara | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  |  | VPN Feature (confusing) | Changes reflect on master proposal document | Documentation | Christian Lam | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  |  | How will users be notified of changes to titles | Changes reflect on master proposal document | Documentation | Eric Truong | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
[6 empty] | Estimated effort | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0
[6 empty] | Actual effort | 8.66 | 8.66 | 8.33 | 7.5 | 1.5 | 0.5 | 0 | 0
[8 empty] | Sat | Sun | Mon | Tue | Wed | Thur | Fri
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Estimate | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01
1.3 | Edit Proposal | 2021-09-25 | Reformat proposal to appear more professional | Changes reflect on master proposal document | Documentation | Michael Lamera | 1 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
|  |  | Add table of contents | Changes reflect on master proposal document | Documentation | Erina Lara | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
|  |  | Explicitly specify browser version restriction and support | Changes reflect on master proposal document | Documentation | Daniel Monge | 0.5 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0
|  |  | Add user option to opt out of email notifications | Changes reflect on master proposal document | Documentation | Christian Lam | 0.5 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add article age order | Changes reflect on master proposal document | Documentation | Eric Truong | 0.5 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add an Expansion section | Changes reflect on master proposal document | Documentation | Erina Lara | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0
|  |  | Remove implementation details | Changes reflect on master proposal document | Documentation | Christian Lam | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
[6 empty] | Estimated effort | 6 | 5.1429 | 4.2857 | 3.4286 | 2.5714 | 1.7143 | 0.85714 | 0
[6 empty] | Actual effort | 5.16 | 4 | 2.5 | 1 | 0 | 0 | 0 | 0
[8 empty] | Sat | Sun | Mon | Tue | Wed | Thur | Fri
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Estimate | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08
2.1 | BRD, Tech Spec, HL Design, Site Map | 2021-10-02 | BRD - Include project overview | Changes reflect on master BRD | Documentation | Daniel Monge | 1 | 0 | 0.5 | 0 | 1
|  |  | BRD - Glossary of terms | Changes reflect on master BRD | Documentation | Daniel Monge | 2 | 1 | 0.5 | 1 | 0
|  |  | BRD - Business Requirements | Changes reflect on master BRD | Documentation | Daniel Monge | 8 | 2 | 0.5 | 4.5 | 1.5
|  |  | BRD - Use cases | Changes reflect on master BRD | Documentation | Daniel Monge | 8 | 3 | 2.5 | 0 | 3
|  |  | BRD - Complete project details | Changes reflect on master BRD | Documentation | Erina Lara | 10 | 4 | 2 | 2 | 2
|  |  | BRD - Business Requirements | Changes reflect on master BRD | Documentation | Erina Lara | 10 | 3 | 4 | 2 | 1
|  |  | BRD - Use cases | Changes reflect on master BRD | Documentation | Erina Lara | 10 | 0 | 1 | 4 | 5
|  |  | Site Map - Create list of pages | Changes reflect on master Site Map | Documentation | Michael Lamera | 5 | 2 | 2 | 2 | 1
|  |  | Site Map - Create errors for pages | Changes reflect on master Site Map | Documentation | Michael Lamera | 2 | 0 | 0 | 0 | 2
|  |  | HL Design - Design Diagrams | Changes reflect on master HL Design | Documentation | Eric Truong | 5 | 1 | 2 | 1 | 2
|  |  | HL Design - Create decriptions | Changes reflect on master HL Design | Documentation | Eric Truong | 8 | 2 | 2 | 3 | 3
|  |  | Tech Spec - Hardware Requirements | Changes reflect on master Tech Spec | Documentation | Christian Lam | 2 | 1 | 0.5 | 0.5 | 1
|  |  | Tech Spec - General Technology Specifications | Changes reflect on master Tech Spec | Documentation | Christian Lam | 5 | 1 | 2.5 | 1 | 2
|  |  | Tech Spec - Product Technology Specifications | Changes reflect on master Tech Spec | Documentation | Christian Lam | 8 | 2 | 2 | 2 | 3
|  |  | Tech Spec - Security Specifications | Changes reflect on master Tech Spec | Documentation | Christian Lam | 2 | 0 | 0 | 1 | 3
[6 empty] | Estimated effort | 86 | 73.7143 | 61.4286 | 49.1429 | 36.8571 | 24.5714 | 12.2857 | 0
[6 empty] | Actual effort | 98.5 | 76.5 | 54.5 | 30.5 | 0 | 0 | 0 | 0
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity
[9 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | Eric Truong | Estimate | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 |  | Michael Lamera | Estimate | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 |  |  | Estimated Effort | 4 | 3.4286 | 2.8571 | 2.2857 | 1.7143 | 1.1429 | 0.57143 | 0 | Estimated Effort | 4 | 3.4286 | 2.8571 | 2.2857 | 1.7143 | 1.1429 | 0.57143 | 0 |  | Estimated Effort | 3 | 2.5714 | 2.1429 | 1.7143 | 1.2857 | 0.85714 | 0.42857 | 0
3.1 | Network Diagram | 2021-10-07 | Network Diagram - Network Diagram | Changes reflect on master Network Diagram | Documentation | Eric Truong | Eric Truong | 4 | 0 | 1 | 0 | 0 | 1 | 1 | 1 |  | 0 | 1 | 0 | 0 | 1 | 1.5 | 1.5 | Eric Truong | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 |  | Current Done | 4 | 4 | 4 | 2.5 | 1 | 0.5 | 0 | 0 | Current Done | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 0 |  | Current Done | 3 | 3 | 3 | 2 | 2 | 1.5 | 1 | 0
|  |  | Network Diagram - Technologies | Changes reflect on master Network Diagram | Documentation | Christian Lam | Christian Lam | 4 | 0 | 0 | 1.5 | 1.5 | 0.5 | 0.5 | 0 |  | 0 | 0 | 2 | 2 | 1 | 1 | 0 | Christian Lam | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 6
|  |  | Network Diagram - Protocol | Changes reflect on master Network Diagram | Documentation | Erina Lara | Erina Lara | 4 | 0.5 | 0.5 | 0.5 | 1 | 0 | 1.5 | 0 |  | 1 | 1 | 0.5 | 0.5 | 0 | 1 | 0 | Erina Lara | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 5 |  | Daniel Monge | Estimate | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | Erina Lara | Estimate | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
|  |  | Network Diagram - Network Flow | Changes reflect on master Network Diagram | Documentation | Michael Lamera | Michael Lamera | 3 | 0 | 0 | 1 | 0 | 0.5 | 0.5 | 1 |  | 0 | 0 | 1.5 | 0 | 0.5 | 0.5 | 1 | Michael Lamera | 0.5 | 0 | 0 | 0 | 1 | 1 | 0.5 | 3 |  | Estimated Effort | 4.5 | 3.8571 | 3.2143 | 2.5714 | 1.9286 | 1.2857 | 0.64286 | 0 | Estimated Effort | 4 | 3.4286 | 2.8571 | 2.2857 | 1.7143 | 1.1429 | 0.57143 | 0
|  |  | Network Diagram - Network Diagram | Changes reflect on master Network Diagram | Documentation | Daniel Monge | Eric Truong | 4.5 | 0 | 1.5 | 1 | 0 | 0 | 1 | 1 |  | 0 | 1 | 1.5 | 0 | 0 | 1 | 0.25 | Daniel Monge | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 5 |  | Current Done | 4.5 | 4.5 | 3 | 2 | 2 | 2 | 1 | 0 | Current Done | 4 | 3.5 | 3 | 2.5 | 1.5 | 1.5 | 0 | 0
[7 empty] | Estimated Effort | 19.5 | 16.7143 | 13.9286 | 11.1429 | 8.3571 | 5.5714 | 2.7857 | 0 | [7 empty] | 22.25 |  | 1. Weeks Capacity Total: 24
[7 empty] | Work Left | 19.5 | 19 | 16 | 12 | 9.5 | 7.5 | 3 | 0
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity Thur: 1. Weeks Capacity
[9 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | Eric Truong | Estimate | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 |  | Michael Lamera | Estimate | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 |  | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 |  | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 |  |  | Estimated Effort | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0 | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 |  | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0
3.2 | Project Plan | 2021-10-14 | Project Plan - Overview | Changes reflect on master Project Plan | Documentation | Daniel Monge | Daniel Monge | 2 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | Eric Truong | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 |  | Current Done | 8 | 8 | 8 | 6 | 4.5 | 2.75 | 0 | 0 | Current Done | 5 | 4 | 4 | 4 | 4 | 3 | 1.5 | 0 |  | Current Done | 5 | 4.5 | 4 | 4 | 4 | 3 | 2 | 0
|  |  | Network Diagram - Network Flow | Changes reflect on master Network Diagram | Documentation | Daniel Monge | Michael Lamera | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Christian Lam | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 10
|  |  | Project Plan - Resources | Changes reflect on master Project Plan | Documentation | Daniel Monge | Daniel Monge | 1.5 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.75 |  | 0 | 0.5 | 0 | 0 | 0 | 0.25 | 1 | Erina Lara | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 5
|  |  | Project Plan - Risk Assessment Risks | Changes reflect on master Project Plan | Documentation | Eric Truong | Eric Truong | 3 | 0.5 | 0 | 0 | 0 | 0.5 | 1 | 1 |  | 1 | 0 | 0 | 0 | 1 | 1.5 | 1.5 | Michael Lamera | 1 | 0.5 | 0 | 0 | 1 | 1 | 1.5 | 5 |  | Daniel Monge | Estimate | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | Erina Lara | Estimate | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20
|  |  | Project Plan - Risk Assessment Risks | Changes reflect on master Project Plan | Documentation | Michael Lamera | Eric Truong | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Daniel Monge | 2.5 | 2 | 0 | 0 | 1 | 0 | 1.5 | 7 |  | Estimated Effort | 6.5 | 5.5714 | 4.6429 | 3.7143 | 2.7857 | 1.8571 | 0.92857 | 0 | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0
|  |  | Project Plan - Risk Assessment Mitigations | Changes reflect on master Project Plan | Documentation | Christian Lam | Christian Lam | 6 | 0 | 0 | 1.5 | 1 | 1.5 | 2 | 0 |  | 0 | 0 | 1.5 | 1 | 1.75 | 2 | 0 |  | 1. Weeks Capacity Total: 32 |  | Current Done | 6.5 | 2 | 1.5 | 1.5 | 1.5 | 0.75 | 0.75 | 0 | Current Done | 5 | 4.25 | 2.5 | 1.5 | 1 | 1 | 0 | 0
|  |  | Project Plan - Timeline | Changes reflect on master Project Plan | Documentation | Erina Lara | Erina Lara | 2 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0.5 | 0 |  | 0.5 | 0.5 | 0.5 | 0 | 0 | 0.25 | 0
|  |  | Project Plan - Timeline | Changes reflect on master Project Plan | Documentation | Michael Lamera | Erina Lara | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0
|  |  | Project Plan - Roadmap | Changes reflect on master Project Plan | Documentation | Erina Lara | Erina Lara | 3 | 0.25 | 1.25 | 0.5 | 0.5 | 0 | 0.5 | 0 |  | 0.5 | 1 | 0.5 | 0.5 | 0 | 0.5 | 0
|  |  | Project Plan - Hour Sprint Distribution | Changes reflect on master Project Plan | Documentation | Eric Truong | Eric Truong | 2 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 |  | 1 | 0 | 0 | 0 | 1 | 1 | 1
|  |  | Project Plan - Project Maintenance and Control | Changes reflect on master Project Plan | Documentation | Michael Lamera | Michael Lamera | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
|  |  | Project Plan - References | Changes reflect on master Project Plan | Documentation | Christian Lam | Christian Lam | 2 | 0 | 0 | 0.5 | 0.5 | 0.25 | 0.75 | 0 |  | 0 | 0 | 0.75 | 0.75 | 0.5 | 1 | 0
[7 empty] | Estimated Effort | 29.5 | 25.2857 | 21.0714 | 16.8571 | 12.6429 | 8.4286 | 4.2143 | 0 | [7 empty] | 32.75
[7 empty] | Work Left | 29.5 | 22.75 | 20 | 17 | 15 | 10.5 | 4.25 | 0
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity Thur: 1. Weeks Capacity
[9 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | Eric Truong | Estimate | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 |  | Michael Lamera | Estimate | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 |  |  | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 |  | Estimated Effort | 3.5 | 3 | 2.5 | 2 | 1.5 | 1 | 0.5 | 0
3.3 | Test Plan | 2021-10-21 | Test Plan - Test Policy, Overview | Changes reflect on master Test Plan | Documentation | Daniel Monge | Daniel Monge | 5 | 0 | 0 | 3 | 2 | 0 | 0 | 0 |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | Eric Truong | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 |  | Current Done | 5 | 5 | 5 | 3.75 | 2.5 | 1.5 | 0 | 0 | Current Done | 5 | 4 | 3 | 3 | 3 | 2 | 1 | 0 |  | Current Done | 3.5 | 3 | 2.5 | 2.5 | 2.5 | 1.5 | 0 | 0
|  |  | Test Plan - Feature Level Scenarios - Logging/Archiving, Datastore, User Interface (UI) Testing | Changes reflect on master Test Plan | Documentation | Christian Lam | Christian Lam | 5 | 0 | 0 | 1.25 | 1.25 | 1 | 1.5 | 0 |  | 0 | 0 | 1.25 | 1.25 | 1 | 1 | 0 | Christian Lam | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 8
|  |  | Test Plan - Feature Level Scenarios - Central Media Library, Playlists Testing | Changes reflect on master Test Plan | Documentation | Eric Truong | Eric Truong | 5 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1.5 | 1.5 | 0 | 0 | 1.5 | 1.5 | 1.5 | Erina Lara | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 5 |  | Daniel Monge | Estimate | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | Erina Lara | Estimate | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27
|  |  | Test Plan - Feature Level Scenarios - Registration, User Management, Login, Logout Testing | Changes reflect on master Test Plan | Documentation | Erina Lara | Erina Lara | 5 | 1 | 1.5 | 1 | 1 | 0 | 0.5 | 0 |  | 2 | 2 | 1.25 | 1 | 0 | 0.5 | 0 | Michael Lamera | 0.5 | 0.5 | 0 | 0 | 2 | 1 | 1 | 5 |  | Estimated Effort | 1 | 0.85714 | 0.71429 | 0.57143 | 0.42857 | 0.28571 | 0.14286 | 0 | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0
|  |  | Test Plan - Feature Level Scenarios - Blacklist, Ratings and Reviews Testing | Changes reflect on master Test Plan | Documentation | Michael Lamera | Michael Lamera | 2.5 | 0.5 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0.5 | 0 | 0 | 0 | 1 | 1 | 0 | Daniel Monge | 0 | 1 | 1 | 4 | 0 | 0 | 2.5 | 8.5 |  | Current Done | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | Current Done | 5 | 4 | 2.5 | 1.5 | 0.5 | 0.5 | 0 | 0
|  |  | Test Plan - Feature Level Scenarios - ActWiki, News Testing | Changes reflect on master Test Plan | Documentation | Daniel Monge | Daniel Monge | 5 | 0 | 1 | 1.5 | 1.5 | 0 | 0 | 1 |  | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1. Weeks Capacity Total: 31.5
|  |  | Test Plan - Document Resources | Changes reflect on master Test Plan | Documentation | Michael Lamera | Michael Lamera | 1 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 |  | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
[7 empty] | Estimated Effort | 28.5 | 24.4286 | 20.3571 | 16.2857 | 12.2143 | 8.1429 | 4.0714 | 0 | [7 empty] | 29.25
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity Thur: 1. Weeks Capacity
[9 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | Eric Truong | Estimate | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 |  | Michael Lamera | Estimate | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 |  | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 |  | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 |  |  | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 | Estimated Effort | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 |  | Estimated Effort | 6 | 5.1429 | 4.2857 | 3.4286 | 2.5714 | 1.7143 | 0.85714 | 0
4.1 | LL Design - User Administration & User Management | 2021-10-28 | User Admin - Registration |  |  | Daniel Monge | Eric Truong | 7 | 2 | 0 | 0 | 2 | 1 | 1 | 1 |  | 2 | 0 | 0 | 1 | 0.5 | 0.5 | 0.5 | Eric Truong | 2 | 2 | 0 | 0 | 1.5 | 1.5 | 1.5 | 8.5 |  | Current Done | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | Current Done | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 2 |  | Current Done | 6 | 5 | 4 | 4 | 4 | 2 | 1 | 0
|  |  | User Admin - Account Deletion |  |  | Christian Lam | Eric Truong | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 2 | 2 | 1.5 | 1.25 | 1.15 | Christian Lam | 0 | 0 | 2 | 2 | 1.5 | 1.25 | 1.15 | 7.9
|  |  | User Management - Creating New User Records |  |  | Michael Lamera | Eric Truong | 6 | 1 | 1 | 0 | 0 | 2 | 1 | 1 |  | 0.5 | 0.5 | 0 | 0 | 1 | 0.5 | 0.5 | Erina Lara | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 6 |  | Daniel Monge | Estimate | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | Erina Lara | Estimate | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03
|  |  | User Management - Modify User Records |  |  | Eric Truong | Eric Truong | 7 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1.5 | 1.5 | 0 | 0 | 1 | 1 | 1.5 | Michael Lamera | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 5 |  | Estimated Effort | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | Estimated Effort | 5.5 | 4.7143 | 3.9286 | 3.1429 | 2.3571 | 1.5714 | 0.78571 | 0
|  |  | User Management - Modify User Records |  |  | Erina Lara | Eric Truong | 5.5 | 0.5 | 1.5 | 1.5 | 2 | 0 | 0 | 0 |  | 2 | 1.5 | 1.5 | 1 | 0 | 0 | 0 | Daniel Monge | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 8 |  | Current Done | 7 | 5 | 5 | 5 | 3 | 2 | 1 | 0 | Current Done | 5.5 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0
35.4
[7 empty] | Estimated Effort | 30.5 | 26.1429 | 21.7857 | 17.4286 | 13.0714 | 8.7143 | 4.3571 | 0 | [7 empty] | 27.9
[7 empty] | Work Left | 30.5 | 26 | 22.5 | 20 | 15 | 10 | 6 | 2
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity Thur: 1. Weeks Capacity
[9 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | Eric Truong | Estimate | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 |  | Michael Lamera | Estimate | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 |  | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 |  | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 |  |  | Estimated Effort | 4.5 | 3.8571 | 3.2143 | 2.5714 | 1.9286 | 1.2857 | 0.64286 | 0 | Estimated Effort | 5.5 | 4.7143 | 3.9286 | 3.1429 | 2.3571 | 1.5714 | 0.78571 | 0 |  | Estimated Effort | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0
4.2 | LL Design - System Observability & Central Media Library | 2021-11-04 | System Observability - Usage Analysis Dashboard |  |  | Erina Lara | Eric Truong | 5 | 0.5 | 1 | 1.5 | 2 | 0 | 0 | 0 |  | 1 | 2 | 1 | 1 | 0 | 0 | 0 | Eric Truong | 1.5 | 1.5 | 0 | 0 | 0 | 1.5 | 1.5 | 6 |  | Current Done | 4.5 | 4.5 | 4.5 | 3.5 | 2 | 0 | 0 | 0 | Current Done | 5.5 | 4 | 2.5 | 2.5 | 2.5 | 2 | 0 | 0 |  | Current Done | 8 | 8 | 6 | 6 | 6 | 4 | 3 | 0
|  |  | System Observability - Logging |  |  | Michael Lamera | Eric Truong | 5 | 0 | 2 | 0 | 0 | 2 | 0 | 1 |  | 0 | 1 | 0 | 0 | 1 | 0 | 0.5 | Christian Lam | 0 | 0 | 1.5 | 2 | 3 | 0 | 0 | 6.5
|  |  | System Observability - Archiving |  |  | Michael Lamera | Eric Truong | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Erina Lara | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 5 |  | Daniel Monge | Estimate | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | Erina Lara | Estimate | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10
|  |  | Central Media Library - Recommended Movies/TV shows |  |  | Christian Lam | Eric Truong | 4.5 | 0 | 0 | 1 | 1.5 | 2 | 0 | 0 |  | 0 | 0 | 1.5 | 2 | 3 | 0 | 0 | Michael Lamera | 0 | 2 | 0 | 0 | 1 | 2 | 1 | 6 |  | Estimated Effort | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0 | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0
|  |  | Central Media Library - Popular Movies/TV Shows |  |  | Daniel Monge | Eric Truong | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | Daniel Monge | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 6 |  | Current Done | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | Current Done | 5 | 4.5 | 3.5 | 2 | 0 | 0 | 0 | 0
|  |  | Central Media Library - Genres |  |  | Eric Truong | Eric Truong | 3 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 |  | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 |  | 1. Weeks Capacity Total: 29.5
|  |  | Central Media Library - Only Movies |  |  | Daniel Monge | Eric Truong | 6 | 2 | 1 | 2 | 1 | 0 | 0 | 0 |  | 2 | 1 | 1 | 1 | 0 | 0 | 0
|  |  | Central Media Library - Only TV shows |  |  | Eric Truong | Eric Truong | 2.5 | 0 | 0 | 0 | 0 | 0.5 | 2 | 0 |  | 0 | 0 | 0 | 0 | 1 | 2 | 0
[7 empty] | Estimated Effort | 31 | 26.5714 | 22.1429 | 17.7143 | 13.2857 | 8.8571 | 4.4286 | 0 | [7 empty] | 29
[7 empty] | Work Left | 31 | 26 | 19.5 | 15 | 10.5 | 6 | 3 | 0
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity Thur: 1. Weeks Capacity
[9 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | Eric Truong | Estimate | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 |  | Michael Lamera | Estimate | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 |  | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 |  | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 |  |  | Estimated Effort | 4.5 | 3.8571 | 3.2143 | 2.5714 | 1.9286 | 1.2857 | 0.64286 | 0 | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 |  | Estimated Effort | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
4.3 | LL Design - Playlists | 2021-11-11 | Playlist - Playlist Creation |  |  | Eric Truong | Eric Truong | 2 | 0.5 | 0.5 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 | 0 | Eric Truong | 2 | 2 | 0 | 0 | 0 | 3 | 1 | 8 |  | Current Done | 4.5 | 4.5 | 4.5 | 3 | 2 | 1 | 0 | 0 | Current Done | 5 | 4.25 | 3.5 | 3.5 | 3.5 | 3.5 | 1 | 0 |  | Current Done | 7 | 6 | 4 | 4 | 4 | 3 | 2 | 0
|  |  | Playlist - Playlist Deletion |  |  | Erina Lara | Eric Truong | 3 | 0.25 | 0.25 | 1 | 1.5 | 0 | 0 | 0 |  | 0.5 | 0.5 | 2 | 1 | 0 | 0 | 0 | Christian Lam | 0 | 0 | 3 | 2 | 2 | 2 | 0 | 9
|  |  | Playlist - Adding Playlist Contributor |  |  | Eric Truong | Eric Truong | 3 | 0.25 | 0.25 | 0 | 0 | 0 | 1.5 | 1 |  | 1 | 0.5 | 0 | 0 | 0 | 1.5 | 1 | Erina Lara | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 4 |  | Daniel Monge | Estimate | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | Erina Lara | Estimate | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17
|  |  | Playlist - Removing Playlist Contributor |  |  | Christian Lam | Eric Truong | 2.5 | 0 | 0 | 1 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0 | 1.5 | 1 | 1 | 1 | 0 | Michael Lamera | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 5 |  | Estimated Effort | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | Estimated Effort | 3 | 2.5714 | 2.1429 | 1.7143 | 1.2857 | 0.85714 | 0.42857 | 0
|  |  | Playlist - Inserting Media into Playlist |  |  | Daniel Monge | Eric Truong | 7 | 1 | 2 | 2 | 1 | 1 | 0 | 0 |  | 0.5 | 1.5 | 1.5 | 1 | 0.5 | 0 | 0 | Daniel Monge | 1 | 3 | 3 | 2 | 1 | 0 | 0 | 10 |  | Current Done | 14 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | Current Done | 3 | 2.75 | 2.5 | 1.5 | 0 | 0 | 0 | 0
|  |  | Playlist - Removing Media from Playlist |  |  | Daniel Monge | Eric Truong | 7 | 1 | 2 | 2 | 1 | 1 | 0 | 0 |  | 0.5 | 1.5 | 1.5 | 1 | 0.5 | 0 | 0 |  | 1. Weeks Capacity Total: 36
|  |  | Playlist - Change User's Permissions |  |  | Michael Lamera | Eric Truong | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0.5 | 1 | 2
|  |  | Playlist - Opt-in/out of Playlist Notifications |  |  | Christian Lam | Eric Truong | 2 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0
|  |  | Playlist - Access Playlists |  |  | Michael Lamera | Eric Truong | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0
[7 empty] | Estimated Effort | 33.5 | 28.7143 | 23.9286 | 19.1429 | 14.3571 | 9.5714 | 4.7857 | 0 | [7 empty] | 35
[7 empty] | Work Left | 33.5 | 29.5 | 22.5 | 16 | 11.5 | 7.5 | 3 | 0
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity Thur: 1. Weeks Capacity
Note: Thanks Giving break 11/20 - 11/28 | [8 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | Eric Truong | Estimate | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 |  | Michael Lamera | Estimate | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 |  | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 |  | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 |  |  | Estimated Effort | 4 | 3.4286 | 2.8571 | 2.2857 | 1.7143 | 1.1429 | 0.57143 | 0 | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 |  | Estimated Effort | 4 | 3.4286 | 2.8571 | 2.2857 | 1.7143 | 1.1429 | 0.57143 | 0
4.4 | LL Design - Blacklists | 2021-11-18 | Blacklist - View Blacklist |  |  | Christian Lam | Eric Truong | 4 | 0 | 0 | 1 | 1 | 1.5 | 0.5 | 0 |  | 0 | 0 | 1.5 | 1.5 | 2 | 1 | 0 | Eric Truong | 1 | 1 | 0 | 0 | 1 | 1.5 | 2 | 6.5 |  | Current Done | 4 | 4 | 4 | 3 | 2 | 0.5 | 0 | 0 | Current Done | 5 | 4.5 | 4 | 4 | 4 | 3.5 | 2 | 0 |  | Current Done | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 0
|  |  | Blacklist - Add actor/actress to Blacklist |  |  | Erina Lara | Eric Truong | 5 | 0 | 1 | 1.5 | 1.5 | 1 | 0 | 0 |  | 0 | 1 | 1 | 1 | 1 | 0 | 0 | Christian Lam | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 8
|  |  | Blacklist - Remove actor/actress from blacklist |  |  | Erina Lara | Eric Truong | 5 | 1 | 1.5 | 1 | 1.5 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Erina Lara | 1 | 2 | 2 | 1 | 1 | 1 | 0 | 8 |  | Daniel Monge | Estimate | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | Erina Lara | Estimate | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24
|  |  | Blacklist - Add a genre to blacklist |  |  | Michael Lamera | Eric Truong | 4 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0.5 | 0.5 | Michael Lamera | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 4 |  | Estimated Effort | 6 | 5.1429 | 4.2857 | 3.4286 | 2.5714 | 1.7143 | 0.85714 | 0 | Estimated Effort | 10 | 8.5714 | 7.1429 | 5.7143 | 4.2857 | 2.8571 | 1.4286 | 0
|  |  | Blacklist - Remove genre from blacklist |  |  | Daniel Monge | Eric Truong | 6 | 0 | 1 | 0 | 2 | 2 | 0.5 | 0.5 |  | 0 | 2 | 0 | 2 | 2 | 0.5 | 0.5 | Daniel Monge | 0 | 2 | 0 | 2 | 2 | 1 | 1 | 8 |  | Current Done | 6 | 6 | 5 | 5 | 3 | 1 | 0.5 | 0 | Current Done | 10 | 9 | 6.5 | 4 | 1 | 0 | 0 | 0
|  |  | Blacklist - Enable/Disable user's blacklist |  |  | Eric Truong | Eric Truong | 5 | 0.5 | 0.5 | 0 | 0 | 0.5 | 1.5 | 2 |  | 1 | 1 | 0 | 0 | 1 | 1.5 | 2 |  | 1. Weeks Capacity Total: 34.5
[7 empty] | Estimated Effort | 29 | 24.8571 | 20.7143 | 16.5714 | 12.4286 | 8.2857 | 4.1429 | 0 | [7 empty] | 30.5
[7 empty] | Work Left | 29 | 26.5 | 21.5 | 18 | 12 | 7 | 3.5 | 0
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity Thur: 1. Weeks Capacity
Note: Thanks Giving break 11/20 - 11/28 | [8 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Eric Truong | Estimate | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 |  | Michael Lamera | Estimate | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 |  | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 |  | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 |  |  | Estimated Effort | 3 | 2.5714 | 2.1429 | 1.7143 | 1.2857 | 0.85714 | 0.42857 | 0 | Estimated Effort | 3 | 2.5714 | 2.1429 | 1.7143 | 1.2857 | 0.85714 | 0.42857 | 0 |  | Estimated Effort | 4.5 | 3.8571 | 3.2143 | 2.5714 | 1.9286 | 1.2857 | 0.64286 | 0
4.5 | LL Design - Ratings and Reviews | 2021-11-25 | Ratings and Reviews - Select a Rating |  |  | Eric Truong | Eric Truong | 3 | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1.5 | 1 | 0 | 0 | 0 | 1 | 0 | Eric Truong | 1.5 | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 4.5 |  | Current Done | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | Current Done | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 |  | Current Done | 4.5 | 4 | 3 | 1 | 0 | 0 | 0 | 0
|  |  | Ratings and Reviews - Write a Review |  |  | Erina Lara | Eric Truong | 5 | 0.5 | 0.5 | 1 | 1 | 0 | 2 | 0 |  | 1 | 1 | 1 | 1 | 0 | 1 | 0 | Christian Lam | 0 | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 4.5
|  |  | Ratings and Reviews - Write a Review |  |  | Michael Lamera | Eric Truong | 4.5 | 0.5 | 1 | 2 | 1 | 0 | 0 | 0 |  | 0.5 | 0.5 | 1 | 1 | 0 | 0 | 0 | Erina Lara | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 5 |  | Daniel Monge | Estimate | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Erina Lara | Estimate | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01
|  |  | Ratings and Reviews - Delete a Review |  |  | Christian Lam | Eric Truong | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 |  | 0 | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | Michael Lamera | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 5 |  | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0
|  |  | Ratings and Reviews - Error Handling |  |  | Daniel Monge | Eric Truong | 5 | 1.5 | 1.5 | 1 | 1 | 0 | 0 | 0 |  | 1.5 | 1.5 | 1 | 1 | 0 | 0 | 0 | Daniel Monge | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 6 |  | Current Done | 5 | 3.5 | 2 | 1 | 0 | 0 | 0 | 0 | Current Done | 5 | 4.5 | 4 | 3 | 2 | 2 | 0 | 0
[7 empty] | Estimated Effort | 20.5 | 17.5714 | 14.6429 | 11.7143 | 8.7857 | 5.8571 | 2.9286 | 0 | [7 empty] | 21 |  | 1. Weeks Capacity Total: 25
[7 empty] | Work Left | 20.5 | 17 | 13 | 8 | 4 | 3 | 0 | 0
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity Thur: 1. Weeks Capacity
[9 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | Eric Truong | Estimate | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 |  | Michael Lamera | Estimate | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 |  | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 |  | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 |  |  | Estimated Effort | 4 | 3.4286 | 2.8571 | 2.2857 | 1.7143 | 1.1429 | 0.57143 | 0 | Estimated Effort | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 |  | Estimated Effort | 9 | 7.7143 | 6.4286 | 5.1429 | 3.8571 | 2.5714 | 1.2857 | 0
4.6 | LL Design - ActWiki & News | 2021-12-02 | ActWiki - Show ActWiki |  |  | Michael Lamera | Eric Truong | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | Eric Truong | 2 | 2 | 0 | 0 | 1.5 | 0.5 | 0.5 | 6.5 |  | Current Done | 4 | 4 | 4 | 2.5 | 1 | 0 | 0 | 0 | Current Done | 5 | 4 | 2.5 | 2.5 | 2.5 | 2.5 | 0.5 | 0 |  | Current Done | 9 | 8 | 7 | 7 | 7 | 4.5 | 2 | 0
|  |  | ActWiki - Search for Actor/Actress |  |  | Christian Lam | Eric Truong | 2.5 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 |  | 0 | 0 | 2 | 1.5 | 1 | 0 | 0 | Christian Lam | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 8
|  |  | News - Publish Article |  |  | Daniel Monge | Eric Truong | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | Erina Lara | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 6 |  | Daniel Monge | Estimate | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | Erina Lara | Estimate | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08
|  |  | News - Delete an Article |  |  | Erina Lara | Eric Truong | 3 | 0.25 | 0.25 | 1 | 1.5 | 0 | 0 | 0 |  | 1 | 0.5 | 1 | 1 | 0 | 0 | 0 | Michael Lamera | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 7 |  | Estimated Effort | 12 | 10.2857 | 8.5714 | 6.8571 | 5.1429 | 3.4286 | 1.7143 | 0 | Estimated Effort | 6 | 5.1429 | 4.2857 | 3.4286 | 2.5714 | 1.7143 | 0.85714 | 0
|  |  | News - Show Article Information |  |  | Eric Truong | Eric Truong | 2 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 |  | 1 | 1 | 0 | 0 | 0 | 0.5 | 0.5 | Daniel Monge | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 10 |  | Current Done | 12 | 11 | 8 | 7 | 7 | 5 | 3 | 1 | Current Done | 6 | 5.25 | 5 | 3 | 1.5 | 0 | 0 | 0
|  |  | News - Show News Page |  |  | Daniel Monge | Eric Truong | 4 | 0 | 1 | 1 | 0 | 2 | 0 | 0 |  | 0 | 2 | 1 | 0 | 2 | 0 | 0 |  | 1. Weeks Capacity Total: 37.5
|  |  | Low Level Design Diagrams editing |  |  | Christian Lam | Eric Truong | 1.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 |  | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0
|  |  | Low Level Design Diagrams editing |  |  | Daniel Monge | Eric Truong | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 |  | 0 | 0 | 0 | 0 | 0 | 1 | 2
|  |  | Low Level Design Diagrams editing |  |  | Eric Truong | Eric Truong | 3 | 0.5 | 1 | 0 | 0 | 0 | 1.5 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 | 0
|  |  | Low Level Design Diagrams editing |  |  | Erina Lara | Eric Truong | 3 | 0.5 | 0 | 1 | 0 | 1.5 | 0 | 0 |  | 0.5 | 0 | 1 | 0 | 1.5 | 0 | 0
|  |  | Low Level Design Diagrams editing |  |  | Michael Lamera | Eric Truong | 7 | 0 | 0 | 0 | 0 | 2.5 | 2.5 | 2 |  | 0 | 0 | 0 | 0 | 2 | 2 | 1
[7 empty] | Estimated Effort | 36 | 30.8571 | 25.7143 | 20.5714 | 15.4286 | 10.2857 | 5.1429 | 0 | [7 empty] | 35.5
[7 empty] | Work Left | 36 | 32.25 | 26.5 | 22 | 19 | 12 | 5.5 | 0
[9 empty] | 3. Productive Hours | [7 empty] | 2. Total Hours Spent | [7 empty] | 1. Weeks Capacity Thur: 1. Weeks Capacity
[9 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  | Christian Lam | Estimate | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | Eric Truong | Estimate | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 |  | Michael Lamera | Estimate | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 |  | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 |  | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 |  |  | Estimated Effort | 25 | 21.4286 | 17.8571 | 14.2857 | 10.7143 | 7.1429 | 3.5714 | 0 | Estimated Effort | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0 |  | Estimated Effort | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
4.7 | UM / Logging / Archiving / Testing Implementation | 2021-12-09 | User Management classes implementation |  |  | Erina Lara | Eric Truong | 30 | 1 | 3 | 6 | 6 | 6 | 6 | 2 |  | 2 | 3 | 6 | 5 | 5 | 5 | 2 | Eric Truong | 4 | 4 | 0 | 0 | 4 | 5 | 2 | 19 |  | Current Done | 25 | 22 | 19 | 14 | 10 | 6 | 2 | 0 | Current Done | 15 | 12 | 9 | 9 | 9 | 5 | 1 | 0 |  | Current Done | 32 | 30 | 26 | 21 | 15 | 9 | 3 | 0
|  |  | User Management Unit Testing |  |  | Michael Lamera | Eric Truong | 16 | 1 | 2 | 2.5 | 3 | 3 | 3 | 1.5 |  | 2 | 3 | 3 | 3 | 3 | 3 | 2 | Christian Lam | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 30
|  |  | Logging and Archiving Unit Testing |  |  | Michael Lamera | Eric Truong | 16 | 1 | 2 | 2.5 | 3 | 3 | 3 | 1.5 |  | 2 | 3 | 3 | 3 | 3 | 3 | 2 | Erina Lara | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 32 |  | Daniel Monge | Estimate | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | Erina Lara | Estimate | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15
|  |  | User Management Unit Testing |  |  | Daniel Monge | Eric Truong | 12 | 0 | 0 | 0 | 3 | 3 | 3 | 3 |  | 0 | 0 | 0 | 3 | 3 | 3 | 3 | Michael Lamera | 2 | 5 | 5 | 5 | 5 | 5 | 2 | 29 |  | Estimated Effort | 33 | 28.2857 | 23.5714 | 18.8571 | 14.1429 | 9.4286 | 4.7143 | 0 | Estimated Effort | 30 | 25.7143 | 21.4286 | 17.1429 | 12.8571 | 8.5714 | 4.2857 | 0
|  |  | Logging and Archiving Unit Testing |  |  | Daniel Monge | Eric Truong | 12 | 0 | 0 | 0 | 3 | 3 | 3 | 3 |  | 0 | 0 | 0 | 3 | 3 | 3 | 3 | Daniel Monge | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 32 |  | Current Done | 33 | 30 | 27 | 24 | 18 | 12 | 6 | 0 | Current Done | 30 | 29 | 26 | 20 | 14 | 8 | 2 | 0
|  |  | Logging implementation |  |  | Eric Truong | Eric Truong | 10 | 3 | 3 | 0 | 0 | 4 | 0 | 0 |  | 4 | 4 | 0 | 0 | 4 | 0 | 0 |  | 1. Weeks Capacity Total: 142
|  |  | Archiving implementation |  |  | Eric Truong | Eric Truong | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  | 0 | 0 | 0 | 0 | 0 | 5 | 2
|  |  | Logging implementation |  |  | Christian Lam | Eric Truong | 15 | 3 | 3 | 3 | 2 | 2 | 2 | 0 |  | 3.5 | 3.5 | 3.5 | 2.5 | 2.5 | 2.5 | 0
|  |  | Archiving implementation |  |  | Christian Lam | Eric Truong | 10 | 0 | 0 | 2 | 2 | 2 | 2 | 2 |  | 0 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
|  |  | Project Setup |  |  | Daniel Monge | Eric Truong | 9 | 3 | 3 | 3 | 0 | 0 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | 0
[7 empty] | Estimated Effort | 135 | 115.7143 | 96.4286 | 77.1429 | 57.8571 | 38.5714 | 19.2857 | 0 | [7 empty] | 151.5
[7 empty] | Work Left | 135 | 123 | 107 | 88 | 66 | 40 | 14 | 0
[9 empty] | 3. Productive Hours | [14 empty] | 2. Total Hours Spent | [19 empty] | 1. Weeks Capacity
[7 empty] | 5.1 |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | [5 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  |  | Christian Lam | Estimate | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | Eric Truong | Estimate | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | Michael Lamera | Estimate | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 |  | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 |  | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | [5 empty] | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 |  | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 |  |  |  | Estimated Effort | 30 | 27.8571 | 25.7143 | 23.5714 | 21.4286 | 19.2857 | 17.1429 | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0 | Estimated Effort | 30 | 27.8571 | 25.7143 | 23.5714 | 21.4286 | 19.2857 | 17.1429 | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0 | Estimated Effort | 30 | 27.8571 | 25.7143 | 23.5714 | 21.4286 | 19.2857 | 17.1429 | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0
5.1 | User Management / ORM | 2021-12-16 | Archiving Compression |  |  | Michael Lamera | Eric Truong | 21 | 0 | 0 | 2 | 2 | 2 | 2 | 2 |  | 2 | 0 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 3 | 2 | 2 | 2 |  | 2 | 0 | 3 | 3 | 0 | 0 | 3 |  |  |  |  | Eric Truong | 3 | 0 | 0 | 0 | 3 | 3 | 3 |  | 4 | 4 | 0 | 0 | 4 | 3 | 3 | 30 |  |  | Current Done | 30 | 29 | 28 | 27 | 26 | 26 | 24 | 22 | 20 | 18 | 14 | 14 | 12 | 10 | 0 | Current Done | 30 | 27 | 27 | 27 | 27 | 24 | 21 | 18 | 14 | 10 | 10 | 10 | 6 | 3 | 0 | Current Done | 30 | 30 | 30 | 28 | 22 | 20 | 18 | 16 | 14 | 14 | 9 | 5 | 5 | 5 | 2
|  |  | User Management Coding Standardization |  |  | Erina Lara | Eric Truong | 25 | 2 | 0 | 2 | 2 | 2 | 2 | 2 |  | 2 | 0 | 3 | 2 | 2 | 2 | 2 | 3 | 0 | 2 | 2 | 2 | 2 | 2 |  | 2 | 0 | 3 | 2 | 2 | 2 | 2 |  |  |  |  | Christian Lam | 1 | 2 | 2 | 1 | 0 | 2 | 2 |  | 2 | 2 | 4 | 0 | 2 | 2 | 10 | 32
|  |  | User Management DAO implementation |  |  | Christian Lam | Eric Truong | 25 | 1 | 1 | 1 | 1 | 0 | 2 | 2 |  | 2 | 2 | 4 | 0 | 2 | 2 | 5 | 1 | 2 | 2 | 1 | 0 | 2 | 2 |  | 2 | 2 | 4 | 0 | 2 | 2 | 5 |  |  |  |  | Erina Lara | 3 | 0 | 2 | 2 | 2 | 2 | 2 |  | 2 | 0 | 6 | 4 | 2 | 2 | 2 | 31 |  |  | Daniel Monge | Estimate | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | Erina Lara | Estimate | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29
|  |  | User Management Testing |  |  | Erina Lara | Eric Truong | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3 | 2 | 0 | 0 | 0 |  |  |  |  | Michael Lamera | 0 | 0 | 3 | 7 | 2 | 2 | 2 |  | 2 | 0 | 6 | 5 | 0 | 0 | 3 | 32 |  |  | Estimated Effort | 30 | 27.8571 | 25.7143 | 23.5714 | 21.4286 | 19.2857 | 17.1429 | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0 | Estimated Effort | 30 | 27.8571 | 25.7143 | 23.5714 | 21.4286 | 19.2857 | 17.1429 | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0
|  |  | User Management Testing |  |  | Michael Lamera | Eric Truong | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3 | 2 | 0 | 0 | 0 |  |  |  |  | Daniel Monge | 5 | 5 | 0 | 0 | 0 | 5 | 0 |  | 0 | 5 | 5 | 0 | 5 | 0 | 0 | 30 |  |  | Current Done | 30 | 25 | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 10 | 5 | 5 | 0 | 0 | 0 | Current Done | 30 | 28 | 28 | 26 | 24 | 22 | 20 | 18 | 16 | 16 | 11 | 8 | 6 | 4 | 2
|  |  | User Management DAO implementation |  |  | Daniel Monge | Eric Truong | 30 | 5 | 5 | 0 | 0 | 0 | 5 | 0 |  | 0 | 5 | 5 | 0 | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 5 | 0 |  | 0 | 5 | 5 | 0 | 5 | 0 | 0 | [13 empty] | Total: 155
|  |  | Logging/Archiving Implementation Revisions |  |  | Eric Truong | Eric Truong | 30 | 3 | 0 | 0 | 0 | 3 | 3 | 3 |  | 4 | 4 | 0 | 0 | 4 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 3 |  | 4 | 4 | 0 | 0 | 4 | 3 | 3
|  |  | ORM DAR |  |  | Christian Lam | Eric Truong | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  | Logging Coding Standardization |  |  | Michael Lamera | Eric Truong | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Archiving Coding Standardization |  |  | Michael Lamera | Eric Truong | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Estimated Effort | 150 | 139.2857 | 128.5714 | 117.8571 | 107.1429 | 96.4286 | 85.7143 | 75 |  | 64.2857 | 53.5714 | 42.8571 | 32.1429 | 21.4286 | 10.7143 | 0 | [14 empty] | 155
[7 empty] | Work Left | 150 | 139 | 133 | 128 | 119 | 112 | 98 | 89 |  | 79 | 68 | 49 | 42 | 29 | 22 | 4
[9 empty] | 3. Productive Hours | [14 empty] | 2. Total Hours Spent | [19 empty] | 1. Weeks Capacity
[7 empty] | 5.2 |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | [5 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  |  | Christian Lam | Estimate | 2022-12-30 | 2022-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | Eric Truong | Estimate | 2022-12-30 | 2022-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | Michael Lamera | Estimate | 2022-12-30 | 2022-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2022-12-30 | 2022-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 |  | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-12-30 | 2022-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 |  | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | [5 empty] | 2022-12-30 | 2022-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 |  | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 |  |  |  | Estimated Effort | 10 | 9.2857 | 8.5714 | 7.8571 | 7.1429 | 6.4286 | 5.7143 | 5 | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 | Estimated Effort | 18 | 16.7143 | 15.4286 | 14.1429 | 12.8571 | 11.5714 | 10.2857 | 9 | 7.7143 | 6.4286 | 5.1429 | 3.8571 | 2.5714 | 1.2857 | 0 | Estimated Effort | 13 | 12.0714 | 11.1429 | 10.2143 | 9.2857 | 8.3571 | 7.4286 | 6.5 | 5.5714 | 4.6429 | 3.7143 | 2.7857 | 1.8571 | 0.92857 | 0
5.2 | User Analysis Dashboard / ORM | 2021-12-30 | User Analysis Dashboard Research |  |  | Erina Lara | Eric Truong | 15 | 0 | 0 | 5 | 5 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 3 | 3 | 2 |  | 2 | 0 | 4 | 1 | 0 | 0 | 0 |  |  |  |  | Eric Truong | 2 | 2 | 0 | 0 | 2 | 3 | 2 |  | 2 | 2 | 0 | 1 | 3 | 3 | 1 | 23 |  |  | Current Done | 10 | 8 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 2 | Current Done | 18 | 16 | 14 | 14 | 14 | 12 | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 5 | Current Done | 13 | 13 | 13 | 12 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 2 | 2
|  |  | User Analysis Dashboard Research |  |  | Christian Lam | Eric Truong | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  |  | Christian Lam | 1 | 1 | 0 | 0 | 2 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 11
|  |  | ORM DAR Research |  |  | Erina Lara | Eric Truong | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6 |  |  |  |  | Erina Lara | 0 | 0 | 2 | 2 | 3 | 3 | 2 |  | 2 | 0 | 2 | 1 | 0 | 0 | 4 | 21 |  |  | Daniel Monge | Estimate | 2022-12-30 | 2022-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | Erina Lara | Estimate | 2022-12-30 | 2022-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12
|  |  | User Analysis Dashboard UI Testing |  |  | Daniel Monge | Eric Truong | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  |  |  |  | Michael Lamera | 0 | 0 | 2 | 2 | 2 | 2 | 2 |  | 2 | 1 | 1 | 0 | 5 | 0 | 0 | 19 |  |  | Estimated Effort | 20 | 18.5714 | 17.1429 | 15.7143 | 14.2857 | 12.8571 | 11.4286 | 10 | 8.5714 | 7.1429 | 5.7143 | 4.2857 | 2.8571 | 1.4286 | 0 | Estimated Effort | 21 | 19.5 | 18 | 16.5 | 15 | 13.5 | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0
|  |  | User Analysis Dashboard UI Testing |  |  | Michael Lamera | Eric Truong | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  |  |  |  | Daniel Monge | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 2 | 2 | 2 | 2 | 4 | 2 | 4 | 20 |  |  | Current Done | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 17 | 16 | 15 | 15 | 15 | 15 | 15 | 15 | Current Done | 21 | 21 | 21 | 16 | 11 | 9 | 9 | 9 | 9 | 9 | 9 | 8 | 7 | 7 | 7
|  |  | User Analysis Dashboard Research |  |  | Daniel Monge | Eric Truong | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 4 | [13 empty] | Total: 94
|  |  | User Analysis Dashboard Research |  |  | Eric Truong | Eric Truong | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 2 | 2 | 0 | 0 | 2 | 2 | 0
|  |  | ORM DAR Research |  |  | Christian Lam | Eric Truong | 8 | 2 | 2 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 3 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 3 | 1 | 1 | 0
|  |  | ORM DAR Research |  |  | Michael Lamera | Eric Truong | 8 | 0 | 0 | 2 | 2 | 1 | 1 | 1 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 |  | 2 | 1 | 1 | 0 | 0 | 0 | 0
|  |  | ORM DAR Research |  |  | Eric Truong | Eric Truong | 8 | 2 | 2 | 0 | 0 | 2 | 2 | 0 |  | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 2 | 3 | 0 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1
[7 empty] | Estimated Effort | 82 | 76.1429 | 70.2857 | 64.4286 | 58.5714 | 52.7143 | 46.8571 | 41 |  | 35.1429 | 29.2857 | 23.4286 | 17.5714 | 11.7143 | 5.8571 | 0 | [14 empty] | 120
[7 empty] | Work Left | 82 | 78 | 74 | 67 | 60 | 54 | 51 | 47 |  | 45 | 43 | 42 | 38 | 34 | 32 | 30
[9 empty] | 3. Productive Hours | [14 empty] | 2. Total Hours Spent | [19 empty] | 1. Weeks Capacity
[7 empty] | 5.3 |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | [5 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  |  | Christian Lam | Estimate | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | Eric Truong | Estimate | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | Michael Lamera | Estimate | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 |  | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 |  | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | [5 empty] | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 |  | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 |  |  |  | Estimated Effort | 20 | 18.5714 | 17.1429 | 15.7143 | 14.2857 | 12.8571 | 11.4286 | 10 | 8.5714 | 7.1429 | 5.7143 | 4.2857 | 2.8571 | 1.4286 | 0 | Estimated Effort | 16 | 14.8571 | 13.7143 | 12.5714 | 11.4286 | 10.2857 | 9.1429 | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0 | Estimated Effort | 23 | 21.3571 | 19.7143 | 18.0714 | 16.4286 | 14.7857 | 13.1429 | 11.5 | 9.8571 | 8.2143 | 6.5714 | 4.9286 | 3.2857 | 1.6429 | 0
5.3 | Registration / ORM | 2022-01-20 | ORM DAR |  |  | Erina Lara | Eric Truong | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Eric Truong | 2 | 2 | 0 | 0 | 2 | 2 | 0 |  | 2 | 1 | 0 | 0 | 0 | 1 | 2 | 14 |  |  | Current Done | 20 | 19 | 19 | 19 | 19 | 18 | 17 | 15 | 15 | 14 | 13 | 13 | 12 | 12 | 12 | Current Done | 16 | 15 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | Current Done | 23 | 22 | 21 | 21 | 21 | 19 | 17 | 15 | 14 | 13 | 13 | 13 | 10 | 7 | 6
|  |  | Registration Coding Standardization |  |  | Eric Truong | Eric Truong | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | Christian Lam | 3 | 3 | 0 | 0 | 2 | 1 | 3.5 |  | 2 | 2 | 0 | 0 | 1 | 1.5 | 1.5 | 20.5
|  |  | Registration Coding |  |  | Michael Lamera | Eric Truong | 16 | 1 | 1 | 0 | 0 | 2 | 2 | 2 |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 |  | 1 | 1 | 0 | 0 | 2 | 2 | 1 |  |  |  |  | Erina Lara | 3 | 0 | 2.5 | 2.5 | 2 | 2 | 4.5 |  | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 24.5 |  |  | Daniel Monge | Estimate | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | Erina Lara | Estimate | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02
|  |  | Registration Testing |  |  | Daniel Monge | Eric Truong | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 1 | 1 |  |  |  |  | Michael Lamera | 1 | 1 | 0 | 0 | 2 | 2 | 1 |  | 1 | 1 | 0 | 0 | 3 | 3 | 2 | 17 |  |  | Estimated Effort | 21 | 19.5 | 18 | 16.5 | 15 | 13.5 | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0 | Estimated Effort | 20 | 18.5714 | 17.1429 | 15.7143 | 14.2857 | 12.8571 | 11.4286 | 10 | 8.5714 | 7.1429 | 5.7143 | 4.2857 | 2.8571 | 1.4286 | 0
|  |  | Registration Testing |  |  | Michael Lamera | Eric Truong | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  |  |  |  | Daniel Monge | 2 | 1 | 1 | 0 | 2 | 1 | 1 |  | 1 | 1 | 1 | 1 | 3 | 1.5 | 1.5 | 18 |  |  | Current Done | 21 | 20 | 19 | 17 | 17 | 15 | 14 | 13 | 11 | 10 | 9 | 8 | 8 | 8 | 8 | Current Done | 20 | 18 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 6 | 4 | 4 | 2 | 0 | 0
|  |  | Registration Coding |  |  | Daniel Monge | Eric Truong | 16 | 1 | 1 | 2 | 0 | 2 | 1 | 1 |  | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 2 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | [13 empty] | Total: 94
|  |  | Logging/Archiving Implementation with Registration |  |  | Eric Truong | Eric Truong | 14 | 1 | 1 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 |  | 2 | 1 | 0 | 0 | 0 | 1 | 0
|  |  | ORM DAR |  |  | Christian Lam | Eric Truong | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Registration Coding |  |  | Erina Lara | Eric Truong | 18 | 2 | 0 | 2 | 2 | 2 | 2 | 0 |  | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 3 | 0 | 2.5 | 2.5 | 2 | 2 | 2 |  | 2 | 0 | 2 | 0 | 2 | 2 | 0
|  |  | Logging/Archiving Implementation with Registration |  |  | Christian Lam | Eric Truong | 18 | 1 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 2 | 1 | 1 |  | 2 | 2 | 0 | 0 | 1 | 1.5 | 1.5
[7 empty] | Estimated Effort | 100 | 92.8571 | 85.7143 | 78.5714 | 71.4286 | 64.2857 | 57.1429 | 50 |  | 42.8571 | 35.7143 | 28.5714 | 21.4286 | 14.2857 | 7.1429 | 0 | [14 empty] | 94
[7 empty] | Work Left | 100 | 94 | 91 | 87 | 85 | 77 | 71 | 64 |  | 59 | 56 | 52 | 51 | 45 | 40 | 37
[9 empty] | 3. Productive Hours | [14 empty] | 2. Total Hours Spent | [19 empty] | 1. Weeks Capacity
[7 empty] | 5.4 |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | [5 empty] | Thur | Fri | Sat | Sun | Mon | Tue | Wed |  | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Total |  |  | Christian Lam | Estimate | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | Eric Truong | Estimate | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | Michael Lamera | Estimate | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 |  | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 |  | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | [5 empty] | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 |  | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 |  |  |  | Estimated Effort | 12 | 11.1429 | 10.2857 | 9.4286 | 8.5714 | 7.7143 | 6.8571 | 6 | 5.1429 | 4.2857 | 3.4286 | 2.5714 | 1.7143 | 0.85714 | 0 | Estimated Effort | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | Estimated Effort | 20 | 18.5714 | 17.1429 | 15.7143 | 14.2857 | 12.8571 | 11.4286 | 10 | 8.5714 | 7.1429 | 5.7143 | 4.2857 | 2.8571 | 1.4286 | 0
5.4 | UI | 2022-02-03 | Homepage UI |  |  | Eric Truong | Eric Truong | 6 | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 1 | 0 |  | 0.5 | 0 | 0 | 0 | 0.5 | 1 | 0 |  |  |  |  | Eric Truong | 3 | 3 | 0 | 0 | 0 | 3 | 0 |  | 2.5 | 0 | 0 | 0 | 1.5 | 2 | 0 | 15 |  |  | Current Done | 12 | 11 | 11 | 10 | 10 | 9 | 9 | 9 | 9 | 7 | 7 | 7 | 7 | 7 | 5 | Current Done | 14 | 12 | 10 | 10 | 10 | 10 | 7 | 7 | 5 | 5 | 5 | 5 | 4 | 3 | 3 | Current Done | 20 | 18 | 16 | 14 | 12 | 10 | 9 | 8 | 6 | 4 | 2 | 1 | 1 | 0 | 0
|  |  | Registration UI |  |  | Erina Lara | Eric Truong | 5 | 1 | 0 | 0 | 0 | 1 | 1 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Christian Lam | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 0 |  | 1 | 2 | 1 | 1 | 1 | 1 | 2.5 | 14
|  |  | Connect UI to Registration |  |  | Daniel Monge | Eric Truong | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 6 | 5 |  |  |  |  | Erina Lara | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  | 1 | 0 | 0 | 0 | 1 | 0 | 2.5 | 9 |  |  | Daniel Monge | Estimate | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | Erina Lara | Estimate | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16
|  |  | Validation |  |  | Christian Lam | Eric Truong | 10 | 1 | 0 | 1 | 0 | 1 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 0 |  | 1 | 2 | 1 | 1 | 1 | 1 | 0 |  |  |  |  | Michael Lamera | 2.5 | 2.5 | 2 | 2 | 2 | 1 | 1 |  | 2 | 2 | 1 | 1 | 0 | 1 | 0 | 20 |  |  | Estimated Effort | 25 | 23.2143 | 21.4286 | 19.6429 | 17.8571 | 16.0714 | 14.2857 | 12.5 | 10.7143 | 8.9286 | 7.1429 | 5.3571 | 3.5714 | 1.7857 | 0 | Estimated Effort | 7 | 6.5 | 6 | 5.5 | 5 | 4.5 | 4 | 3.5 | 3 | 2.5 | 2 | 1.5 | 1 | 0.5 | 0
|  |  | Homepage UI |  |  | Michael Lamera | Eric Truong | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.5 | 2 | 2 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Daniel Monge | 2 | 2 | 2 | 2 | 1 | 1 | 1 |  | 1 | 0 | 0 | 0 | 0 | 6 | 5 | 23 |  |  | Current Done | 25 | 23 | 21 | 19 | 17 | 15 | 14 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 3 | Current Done | 7 | 6 | 6 | 6 | 6 | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 1
|  |  | Registration UI |  |  | Daniel Monge | Eric Truong | 15 | 2 | 2 | 2 | 2 | 2 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 1 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Total: 81
|  |  | Registration UI |  |  | Eric Truong | Eric Truong | 8 | 1 | 1 | 0 | 0 | 0 | 2 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 2 | 0 |  | 2 | 0 | 0 | 0 | 1 | 1 | 0
|  |  | Connect UI to Registration |  |  | Michael Lamera | Eric Truong | 10 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  | 2 | 2 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  | 2 | 2 | 1 | 1 | 0 | 1 | 0
|  |  | ORM DAR |  |  | Erina Lara | Eric Truong | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
|  |  | ORM DAR |  |  | Christian Lam | Eric Truong | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
[7 empty] | Estimated Effort | 78 | 72.4286 | 66.8571 | 61.2857 | 55.7143 | 50.1429 | 44.5714 | 39 |  | 33.4286 | 27.8571 | 22.2857 | 16.7143 | 11.1429 | 5.5714 | 0 | [14 empty] | 81
[7 empty] | Work Left | 78 | 70 | 64 | 59 | 55 | 49 | 43 | 41 |  | 36 | 32 | 30 | 29 | 28 | 21 | 12
[9 empty] | 3. Productive Hours | [14 empty] | 2. Total Hours Spent | [19 empty] | 1. Weeks Capacity | [17 empty] | NOTE
[7 empty] | 6.1 |  | Mon | Tue | Wed | Thur | Fri | Sat | Sun |  | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun |  | Mon | Tue | Wed | Thur | Fri | Sat | Sun | [5 empty] | Mon | Tue | Wed | Thur | Fri | Sat | Sun |  | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Total |  |  | Christian Lam | Estimate | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | Eric Truong | Estimate | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | Michael Lamera | Estimate | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06
Sprint | Story | Sprint Start Date | Tasks | Definition of Done | Category | Who | Responsible Party | Estimate | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 |  | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 |  | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | [5 empty] | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 |  | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 |  |  |  | Estimated Effort | 30 | 27.8571 | 25.7143 | 23.5714 | 21.4286 | 19.2857 | 17.1429 | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0 | Estimated Effort | 30 | 27.8571 | 25.7143 | 23.5714 | 21.4286 | 19.2857 | 17.1429 | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0 | Estimated Effort | 30 | 27.8571 | 25.7143 | 23.5714 | 21.4286 | 19.2857 | 17.1429 | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0
6.1 | Registration / Authorization / Authentication / Log out / UAD | 2022-02-21 | Registration |  |  | Daniel Monge | Eric Truong | 20 | 0 | 0 | 2 | 2 | 2 | 2 | 2 |  | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 2.5 | 1.5 | 2.5 | 1.5 | 2 |  | 0 | 2 | 0 | 2 | 1 | 1 | 0 |  |  |  |  | Eric Truong | 0 | 4 | 3 | 4 | 4 | 0 | 0 |  | 0 | 4 | 3 | 4 | 4 | 0 | 0 | 30 |  |  | Current Done | 30 | 29 | 29 | 27 | 25 | 25 | 25 | 25 | 23 | 23 | 21 | 19 | 19 | 19 | 19 | Current Done | 30 | 30 | 27 | 24 | 21 | 18 | 18 | 18 | 18 | 16 | 14 | 12 | 10 | 10 | 10 | Current Done | 30 | 30 | 29 | 27 | 27 | 27 | 27 | 27 | 27 | 26 | 25 | 24 | 24 | 24 | 24
|  |  | Authorization |  |  | Erina Lara | Eric Truong | 15 | 2 | 2 | 2 | 2 | 0 | 1 | 1 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0.5 | 0.5 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | Christian Lam | 2 | 3 | 2 | 3 | 0 | 2 | 0 |  | 2 | 3 | 2 | 3 | 0 | 4 | 4 | 30
|  |  | Authentication |  |  | Eric Truong | Eric Truong | 15 | 0 | 2 | 2 | 2 | 2 | 0 | 0 |  | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 |  | 0 | 1.5 | 1.5 | 1.5 | 1 | 0 | 0 |  |  |  |  | Erina Lara | 2 | 4 | 2 | 4 | 0 | 2 | 2 |  | 2 | 4 | 2 | 4 | 0 | 4 | 3 | 35 |  |  | Daniel Monge | Estimate | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | Erina Lara | Estimate | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06
|  |  | Log out |  |  | Christian Lam | Eric Truong | 10 | 1 | 0 | 2 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Michael Lamera | 2 | 4 | 2 | 4 | 1 | 1 | 2 |  | 2 | 4 | 2 | 4 | 1 | 0 | 1 | 30 |  |  | Estimated Effort | 35 | 32.5 | 30 | 27.5 | 25 | 22.5 | 20 | 17.5 | 15 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0 | Estimated Effort | 35 | 32.5 | 30 | 27.5 | 25 | 22.5 | 20 | 17.5 | 15 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0
|  |  | UAD |  |  | Michael Lamera | Eric Truong | 20 | 0 | 1 | 2 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 2 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Daniel Monge | 3 | 2 | 2 | 2 | 3 | 3 | 3 |  | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 35 |  |  | Current Done | 35 | 35 | 35 | 33 | 31 | 29 | 27 | 25 | 25 | 23 | 23 | 19 | 16 | 13 | 11 | Current Done | 35 | 32 | 29 | 25 | 22 | 22 | 21 | 20 | 18 | 16 | 14.5 | 12 | 12 | 12 | 9
|  |  | Registration |  |  | Erina Lara | Eric Truong | 20 | 1 | 1 | 2 | 1 | 0 | 0 | 0 |  | 2 | 2 | 1.5 | 1.5 | 0 | 0 | 3 | 1.5 | 0.5 | 2 | 1.5 | 0 | 0 | 0 |  | 2 | 2 | 1.5 | 1.5 | 0 | 0 | 3 | [13 empty] | Total: 160
|  |  | Authorization |  |  | Eric Truong | Eric Truong | 15 | 0 | 1 | 1 | 1 | 1 | 0 | 0 |  | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.5 | 1.5 | 1.5 | 1 | 0 | 0
|  |  | Authentication |  |  | Daniel Monge | Eric Truong | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2.5 | 2 | 2 | 2
|  |  | Log out |  |  | Michael Lamera | Eric Truong | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0
|  |  | UAD |  |  | Christian Lam | Eric Truong | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.5 | 0 | 2.5 | 2.5 | 0 | 0 | 0
[7 empty] | Estimated Effort | 160 | 148.5714 | 137.1429 | 125.7143 | 114.2857 | 102.8571 | 91.4286 | 80 |  | 68.5714 | 57.1429 | 45.7143 | 34.2857 | 22.8571 | 11.4286 | 0 | [14 empty] | 95
[7 empty] | Work Left | 160 | 156 | 149 | 136 | 126 | 121 | 118 | 115 |  | 111 | 104 | 97.5 | 86 | 81 | 78 | 73

## Burndown Charts
| Team Burndown Chart | Christian Lam | Daniel Monge | Eric Truong | Erina Lara | Michael Lamera
3.1
3.2
3.3
4.1
4.2
4.3
4.4
4.5
4.6
4.7
5.1
5.2
5.3
5.4
6.1

## Team Charts
Velocity Chart |  |  | Percent Error
Velocity Summary |  |  | Error Summary
Sprint | Estimated | Actual | Sprint | Error
1.1 | 5.5 | 5.16 | 1.1 | -6.1818
1.2 | 8 | 8.66 | 1.2 | 8.25
1.3 | 6 | 5.16 | 1.3 | -14
2.1 | 86 | 98.5 | 2.1 | 14.5349
3.1 | 19.5 | 22.25 | 3.1 | 14.1026
3.2 | 29.5 | 32.75 | 3.2 | 11.0169
3.3 | 28.5 | 29.25 | 3.3 | 2.6316
4.1 | 30.5 | 27.9 | 4.1 | -8.5246
4.2 | 31 | 29 | 4.2 | -6.4516
4.3 | 33.5 | 35 | 4.3 | 4.4776
4.4 | 29 | 30.5 | 4.4 | 5.1724
4.5 | 20.5 | 21 | 4.5 | 2.439
4.6 | 36 | 35.5 | 4.6 | -1.3889
4.7 | 135 | 151.5 | 4.7 | 12.2222
5.1 | 146 | 155 | 5.1 | 6.1644
5.2 | 52 | 120 | 5.2 | 130.7692
5.3 | 63 | 94 | 5.3 | 49.2063
5.4 | 66 | 81 | 5.4 | 22.7273

## Scrum Meeting Logs
HomeView
Team | Unite
Team Leader | Eric Truong |  | Client
Scrum Master | Daniel Monge |  | V. Vong
Christian Lam
| Erina Lara |  | Master Recording Doc
| Michael Lamera |  | https://docs.google.com/document/d/1HGpNJSTHR37MWrIrR3G-JSfAEZgPhL2g1G9ZjLWqyro/edit?usp=sharing
Sprint Planning Mtg: Thursdays @ 8PM
Sprint Review Mtg: Wednesdays @ 9pm
Meeting Notes
Sprint ID | Story Name | Meeting Date | Length of Meeting | What went well during last sprint? | What went poorly during last sprint? | How will we fix during this sprint?
3.1 | Milestone 2 | 2021-10-07 | 1 hour | - Met the deadline - Good teamwork and communication between team members when working on documents | Miscalculated our capacity - Too much work and not enough time - Worked over our estimated hours Incorrectly designated task responsibilities - Assigned too many people to one task, unclear responsibility Burndown charts didn’t use proper data | Start work earlier Put more thought into measuring our capacity Record our productive hours Record personal estimate and productive hours - Create charts for these Assign a supporter if there are big tasks that require many effort points Fix burndown charts using productive hours and not “actual” hours
3.2 | Milestone 2 | 2021-10-14 | 1 hour | Planning out network diagram components Each working on respective task for network diagram items Finished network diagram Fixed burndown charts Included productive and total hours spent Always have 1 person responsible for a task (others can help) Started estimating our team and individual capacity Started on documents early Started documenting sprint meetings | Temporarily blocked on network diagram Waiting for Vong lecture to discuss networks and https Not much previous knowledge of creating a network diagram Most time spent researching network diagrams | Do research on how the network and ports operates on our own time
3.3 | Milestone 2 | 2021-10-21 | 1 hour | Planning out Test Plan components Designating tasks, responsibilities, and supporters for each member Each working on respective task for project plan items Finished project plan | Unsure about future due dates Unsure about organizing future deliverables for new semester | Create date estimates for the new semester based on our sprint scheduling(?) Organize deliverables in order of priority(?) and then separate them into groups for each milestone
4.1 | Milestone 3 - Low Level Design | 2021-10-27 2021-10-28 | 1 hour | Individual velocity charts Having spread out tasks for each sprint story | Need to separate story items in as individual stories Need to to add responsible party for story backlog Some charts computed wrong/identical info by accident Need to add core components in backlog | Add responsible party under story product backlog Split up core components as separate items in product story backlog Ensure that charts are using the correct columns in order to generate the correct values Add all core components and application feature components in product backlog
4.2 | Milestone 3 - Low Level Design | 2021-11-03 2021-11-04 | 1 hour | Started researching Low Level Design Low Level Document Construction Extended knowledge on abstraction layers, polymorphism, libraries, and networks | Didn’t have a structured research plan for Low Level diagrams Getting blocked due to being unsure of how to go about certain Low Level diagrams Unsure how to do error handling | Separated components and use cases for low level designs Research how to handle specific errors for certain cases Research about what types of classes/layers we would need for our low level designs
4.3 | Milestone 3 - Low Level Design | 2021-11-10 2021-11-11 | 1 hour | Referred to BRD for LLD use cases and error handling Extended knowledge of object oriented design, SOLID | Somewhat difficult to think of errors since some use cases didn’t list any errors Unsure on how to implement security, error handling, and logging into our LLDs | Research common errors for each core component in LLD Research further on how each core component in our LLD should operate based on our BRD
4.4 | Milestone 3 - Low Level Design | 2021-11-17 2021-11-18 | 1 hour | Extended knowledge of dependency inversion control So far, editing LLDs for User Admin, User Management, Observability, Central Media Library, and Playlists | Blocked/delayed because of being unsure about how to implement/go about email notifications for opting in/out of a playlist None of the made LLDs are final, still need to be touched up and further revised | Research how email notifications work Compare LLDs with members to get further input and opinions
4.5 | Milestone 3 - Low Level Design | 2021-11-24 | 1 hour | Extra lecture helped increase understanding of low level designs Got good amount of work done during fall break | Email about sequence diagram resource, miscommunication Some diagrams draw.io and others sequencediagrams.org Some LLDs incorrect after viewing extra lecture | Diagrams from draw.io and sequencediagrams.org look similar enough, so mix of both looks fine Fix LLDs and base them off example from extra lecture
4.6 | Milestone 3 - Low Level Design | 2021-12-01 2021-12-02 | 1 hour | Revised some LLDs Fall break was a good mental reset for the team(ate good) | During fall break, not much work done due to holidays | Put more hours into project
4.7 | Milestone 3 - Implementation | 2021-12-03 | 1 hour | Finished LLDs and turned them in via email Can start implementation of UM, Logging, Archiving, Testing | Realized some designs were not consistent with others When editing LLDs before turn in, BRD does not mention some error handling or use cases Delay on implementation due to requiring approval on LLDs first Error handling on LLDs not adequate Have not started implementation, should’ve finished LLD earlier and started implementation earlier | Communicate with others about how the designs will look Add missing error handling or use cases in BRD More research on error handling Put lots of hours into implementation to finish before deadline
5.1 | Milestone 4 - User Management | 2021-12-15 2021-12-16 | 1 hour | Created implementation for UM, Logging, Archiving, Testing | Implementation doesn't follow coding standards. Source code not organized to match HLD. Missing compression for archiving. Limited tests were created. Need to start ORM DAR | Review coding standards and fix implementations. Revise HLD to match source code. Implement compression for archive. Create more test cases. Revise Project plan.
5.2 | Milestone 4 - User Analysis Dashboard | 2021-12-29 2021-12-30 | 1 hour | ORM DAR started. Continued implementing/revising UM, Archiving, Logging | Winter break / holidays, team spent less hours working on project. | Try to put in more hours when possible during winter break.
5.3 | Milestone 4 - Registration | 2022-01-19 2022-01-20 | 1 hour |  | Was not able to finish most of UAD | Need to research more on UAD
5.4 | Milestone 4 - UI | 2022-02-02 2022-02-03 | 1 hour | Submitted ORM DAR | Blocked due to not having ORM DAR approved.Took a week off to rest before school starts. | Must stay on top of our work.
6.1 | Login/Logout, User Access Control, Central Media Library | 2022-02-14 2022-02-15 | 1 hour | Created implementation for Login/Logout, User Access Control, Central Media Library. ORM DAR approved.
7.1 | Central Media Library, Playlists, Blacklist | 2022-03-14 2022-03-15 | 1 hour | Continue Central Media Library implementation. Created implementation for Playlist, Blacklist
8.1 | Central Media Library, News, ActWiki, Ratings and Reviews | 2022-04-11 2022-04-12 | 1 hour | Continue Central Media Library implementation. Created News, Actwiki, Rating and Reviews

## Check (hidden)
Priority | Status | Category | Person
0 | Dropped | Documentation | Christian Lam
1 | Done! | Domain | Daniel Monge
2 | Blocked | Service | Eric Truong
3 | Ongoing | Presentation | Erina Lara
4 | Planned | Distribution | Michael Lamera
5 |  | Testing | ALL
6 |  | Bug-Fix
7
8
9
10
11
12
13
14
15
16
17
18
19
20